## Planting
Project: | SR 510 Yelm Loop
Address: | SR 510 Yelm Loop New Alignment Phase 2
Scope: | SELF-PERFORM LANDSCAPE – Gold Standard (Raw)
Date: | 2026-06-20
SR# | REF | DESCRIPTION | QTY | UNIT | WASTAGE | QTY W/ WASTAGE | MATERIAL RATE | LABOR RATE | EQUIP RATE | MATERIAL COSTS | LABOR COSTS | EQUIP COSTS | SUB COST
DIV 01 – MOBILIZATION / GENERAL REQUIREMENTS (LIMITED SCOPE)
1 |  | Mobilization / Demobilization – Planting Crew | 1 | LS | 0 | 1 | 0 | 3000 | 800 | 0 | 3000 | 800 | 3800
2 |  | Project Foreman – PLA/Prevailing Wage (4 weeks) | 160 | HR | 0 | 160 | 0 | 75 | 0 | 0 | 12000 | 0 | 12000
3 |  | Safety Orientation / WSDOT Site Training | 1 | EA | 0 | 1 | 300 | 2000 | 0 | 300 | 2000 | 0 | 2300
4 |  | Submittal Preparation – Plant List & Soil Amendments | 1 | LS | 0 | 1 | 0 | 2500 | 0 | 0 | 2500 | 0 | 2500
5 |  | Site Cleanup & Final Demobilization | 1 | LS | 0 | 1 | 200 | 1500 | 400 | 200 | 1500 | 400 | 2100
SUBTOTAL – GEN REQ | [12 empty] | 22700
DIV 32 – UPLAND PLANT MIX (UP) – Container Stock
1 | 32000 | Western Serviceberry (Amelanchier alnifolia) – #2 Cont. | 32 | EA | 0 | 32 | 18 | 9 | 0 | 576 | 288 | 0 | 864
2 | 32000 | Cascara (Frangula purshiana) – #2 Cont. | 32 | EA | 0 | 32 | 18 | 9 | 0 | 576 | 288 | 0 | 864
3 | 32000 | Red Oak (Quercus rubra) – #2 Cont. (12-24" HT) | 35 | EA | 0 | 35 | 65 | 18 | 0 | 2275 | 630 | 0 | 2905
4 | 32000 | Oceanspray (Holodiscus discolor) – #1 Cont. | 822 | EA | 0 | 822 | 14 | 7 | 0 | 11508 | 5754 | 0 | 17262
5 | 32000 | Red-Flowering Currant (Ribes sanguineum) – #1 Cont. | 1096 | EA | 0 | 1096 | 14 | 7 | 0 | 15344 | 7672 | 0 | 23016
6 | 32000 | Nootka Rose (Rosa nutkana) – #1 Cont. | 822 | EA | 0 | 822 | 12 | 7 | 0 | 9864 | 5754 | 0 | 15618
SUBTOTAL – UPLAND PLANT MIX | [12 empty] | 60529
DIV 32 – RIPARIAN PLANT MIX (RP) – Container Stock
1 | 32000 | Oceanspray (Holodiscus discolor) – #1 Cont. | 252 | EA | 0 | 252 | 14 | 7 | 0 | 3528 | 1764 | 0 | 5292
2 | 32000 | Red-Flowering Currant (Ribes sanguineum) – #1 Cont. | 252 | EA | 0 | 252 | 14 | 7 | 0 | 3528 | 1764 | 0 | 5292
3 | 32000 | Nootka Rose (Rosa nutkana) – #1 Cont. | 252 | EA | 0 | 252 | 12 | 7 | 0 | 3024 | 1764 | 0 | 4788
4 | 32000 | Salmonberry (Rubus spectabilis) – #1 Cont. | 252 | EA | 0 | 252 | 14 | 7 | 0 | 3528 | 1764 | 0 | 5292
5 | 32000 | Red Elderberry (Sambucus racemosa) – #1 Cont. | 252 | EA | 0 | 252 | 14 | 7 | 0 | 3528 | 1764 | 0 | 5292
SUBTOTAL – RIPARIAN PLANT MIX | [12 empty] | 25956
DIV 32 – LIVE STAKES (LS) – Willow & Dogwood
1 | 32000 | Red-Osier Dogwood (Cornus sericea) – 24-48" LIVE STAKE @ 3' o.c. | 82 | EA | 0 | 82 | 5.5 | 4.5 | 0 | 451 | 369 | 0 | 820
2 | 32000 | Hooker's Willow (Salix hookeriana) – 24-48" LIVE STAKE @ 3' o.c. | 163 | EA | 0 | 163 | 5.5 | 4.5 | 0 | 896.5 | 733.5 | 0 | 1630
3 | 32000 | Sitka Willow (Salix sitchensis) – 24-48" LIVE STAKE @ 3' o.c. | 163 | EA | 0 | 163 | 5.5 | 4.5 | 0 | 896.5 | 733.5 | 0 | 1630
SUBTOTAL – LIVE STAKES | [12 empty] | 4080
DIV 32 – PLANT LAYOUT / LOCALIZED SOIL AMENDMENT / MULCH RINGS
1 | 32000 | Plant Layout & Staking (field locate per plan) | 1 | LS | 0 | 1 | 0 | 4800 | 0 | 0 | 4800 | 0 | 4800
2 | 32000 | Localized Planting Soil / Amendment (per plant pit – avg 2 CF/plant) | 4099 | CF | 0 | 4099 | 0.45 | 0.2 | 0 | 1844.55 | 819.8 | 0 | 2664.35
3 | 32000 | Mulch Rings / Plant Saucers (3" depth, 24" dia, per plant) | 4099 | EA | 0 | 4099 | 0.18 | 0.12 | 0 | 737.82 | 491.88 | 0 | 1229.7
4 | 32000 | Landscape Punch-List / Deficiency Walk & Correction | 1 | LS | 0 | 1 | 0 | 2800 | 0 | 0 | 2800 | 0 | 2800
SUBTOTAL – LAYOUT / SOIL / MULCH RINGS | [12 empty] | 11494.05
PLANTING TAB – TOTAL RAW COST (Base Bid) | [12 empty] | 124759.05
⛔ EXCLUDED FROM THIS SHEET (per Rev-04 scope): Hydroseeding, full-site seeding, full-site bark mulch, fine grading, topsoil stripping, CAVFS, MVFS, CABS, bioretention, underdrain, check dams, irrigation, temp watering, traffic control, TESC beyond GS work area, civil earthwork.

## Commercial
Project: | SR 510 Yelm Loop
Address: | SR 510 Yelm Loop New Alignment Phase 2
Scope: | SELF-PERFORM LANDSCAPE – Gold Standard (Raw)
Date: | 2026-06-20
SR# | REF | DESCRIPTION | BASIS | RATE | UNIT | QTY | UNIT COST | SUB COST
DIV 01 – COMMERCIAL CARRY / GENERAL REQUIREMENTS (LIMITED SCOPE ONLY)
1 |  | General Liability Insurance | % of contract value (1.5%) | 0.015 | LS | 1 | 4500 | 4500
2 |  | Performance & Payment Bond | % of contract value (1.5%) | 0.015 | LS | 1 | 5000 | 5000
3 |  | Mobilization / Demob (Landscape Crew Only) | Lump Sum |  | LS | 1 | 3800 | 3800
4 |  | Project Foreman – Site Supervision (4 Weeks PLA) | 4 wks × $4,800/wk | 4800 | WK | 4 | 4800 | 19200
5 |  | Certified Payroll Administration (WSDOT/PLA) | 20 hrs @ $150/hr | 150 | HR | 20 | 150 | 3000
6 |  | WSDOT Compliance / Submittal Administration | Lump Sum |  | LS | 1 | 3500 | 3500
7 |  | Submittals / RFI Administration | Lump Sum |  | LS | 1 | 2500 | 2500
8 |  | Closeout Documentation / As-Builts | Lump Sum |  | LS | 1 | 1800 | 1800
9 |  | Landscape Punch-List Administration | Lump Sum |  | LS | 1 | 1200 | 1200
10 |  | Small Tools & Consumables Allowance | Allowance |  | LS | 1 | 1500 | 1500
COMMERCIAL CARRY – SUBTOTAL | [7 empty] | 46000
⚠ NOTE: Rev-04 commercial carry is scaled to a limited planting-only scope (~$300K–$500K). Full-scope commercial carry from Rev-03 ($260K) is NOT applicable here. Insurance and bond carried as flat amounts scaled to this package.

## Establishment
Project: | SR 510 Yelm Loop
Address: | SR 510 Yelm Loop New Alignment Phase 2
Scope: | SELF-PERFORM LANDSCAPE – Gold Standard (Raw)
Date: | 2026-06-20
SR# | REF | DESCRIPTION | DURATION | QTY | UNIT | WASTAGE | QTY W/ WASTAGE | MAT RATE | LAB RATE | EQ RATE | MAT COST | LAB COST | EQ COST | SUB COST
DIV 01 – CLOSEOUT / DOCUMENTATION
1 |  | Closeout Documentation / As-Builts (carried once in Commercial tab – not duplicated here) | End of project | 1 | LS | 0 | 1 | 0 | 1800 | 0 | 0 | 1800 | 0 | 1800
SUBTOTAL – CLOSEOUT | [13 empty] | 1800
DIV 32 – PLANT ESTABLISHMENT & MAINTENANCE (BASE BID – YEAR 1 + YEAR 2)
1 | 32000 | Plant Establishment Period – Year 1 (labor, materials, watering) | 12 months | 1 | LS | 0 | 1 | 3000 | 10000 | 1000 | 3000 | 10000 | 1000 | 14000
2 | 32000 | Plant Establishment Period – Year 2 (if required per spec) | 12 months | 1 | LS | 0 | 1 | 1500 | 6000 | 800 | 1500 | 6000 | 800 | 8300
3 | 32000 | Weed Control / Maintenance Visits (18 visits × 4 hrs) | Per visit | 18 | Visit | 0 | 18 | 0 | 280 | 0 | 0 | 5040 | 0 | 5040
4 | 32000 | Fertilization Applications – Establishment Period (4 applications) | Per app | 4 | APP | 0 | 4 | 350 | 250 | 0 | 1400 | 1000 | 0 | 2400
5 | 32000 | Plant Replacement Allowance (warranty – 10% of plants) | Warranty | 1 | LS | 0 | 1 | 3500 | 1500 | 0 | 3500 | 1500 | 0 | 5000
6 | 32000 | Re-seeding Failed Areas – Localized Only (warranty allowance) | Warranty | 1 | LS | 0 | 1 | 800 | 600 | 0 | 800 | 600 | 0 | 1400
7 | 32000 | Final Inspection & WSDOT Acceptance Walk | End of warranty | 1 | LS | 0 | 1 | 0 | 1800 | 0 | 0 | 1800 | 0 | 1800
SUBTOTAL – ESTABLISHMENT (BASE BID – YR 1 & YR 2) | [13 empty] | 37940
★ ADD-ALTERNATE AA-03 – YEAR 3 PLANT ESTABLISHMENT (NOT IN BASE BID)
2A | 32000 | Plant Establishment Period – Year 3 (ADD-ALTERNATE AA-03 – if required by spec) | 12 months | 1 | LS | 0 | 1 | 1200 | 4500 | 300 | 1200 | 4500 | 300 | 6000
ADD-ALTERNATE AA-03 TOTAL (Year 3 Establishment – NOT in base bid) | [13 empty] | 6000
ESTABLISHMENT TAB – TOTAL RAW COST (BASE BID, Yr1+Yr2 only) | [13 empty] | 39740

## Add-Alternates
Project: | SR 510 Yelm Loop
Address: | SR 510 Yelm Loop New Alignment Phase 2
Scope: | SELF-PERFORM LANDSCAPE – Gold Standard (Raw)
Date: | 2026-06-20
SR# | REF | DESCRIPTION | QTY | UNIT | WASTAGE | QTY W/ WASTAGE | MAT RATE | LAB RATE | EQ RATE | MAT COST | LAB COST | EQ COST | SUB COST
★ ADD-ALTERNATE AA-01 – CAVFS ONLY (Compost Amended Vegetated Filter Strip, 2.66 AC)
1 | 32000 | CAVFS – Compost Amended Vegetated Filter Strip prep & install (2.66 AC = 115,870 SF) | 115870 | SF | 0 | 115870 | 0.85 | 0.22 | 0 | 98489.5 | 25491.4 | 0 | 123980.9
2 | 32000 | CAVFS – Fine Grading / Surface Prep (included in CAVFS unit rate) | 115870 | SF | 0 | 115870 | 0 | 0.05 | 0.04 | 0 | 5793.5 | 4634.8 | 10428.3
AA-01 SUBTOTAL – CAVFS RAW COST | [12 empty] | 134409.2
★ ADD-ALTERNATE AA-02 – CABS / BIORETENTION LIMITED INTERFACE (0.10 AC + 0.83 AC)
1 | 32000 | CABS – Compost Amended Biofiltration Swale install (0.10 AC = 4,356 SF) | 4356 | SF | 0 | 4356 | 5.28 | 3 | 0 | 22999.68 | 13068 | 0 | 36067.68
2 | 32000 | Biofiltration Area Prep & Grading (0.83 AC = 36,155 SF) | 36155 | SF | 0 | 36155 | 0 | 0.25 | 0 | 0 | 9038.75 | 0 | 9038.75
3 | 32000 | Check Dam / Flow Spreader Installation (150 EA, per bioretention detail) | 150 | EA | 0 | 150 | 180 | 40 | 0 | 27000 | 6000 | 0 | 33000
4 | 32000 | Underdrain Piping – Landscape Bioretention Interface (assumed 359 LF, confirm civil) | 359 | LF | 0 | 359 | 180 | 38 | 0 | 64620 | 13642 | 0 | 78262
AA-02 SUBTOTAL – CABS/BIORETENTION RAW COST | [12 empty] | 156368.43
★ ADD-ALTERNATE AA-03 – YEAR 3 PLANT ESTABLISHMENT (if required by spec)
1 | 32000 | Plant Establishment Period – Year 3 (12 months, reduced frequency) | 1 | LS | 0 | 1 | 1200 | 4500 | 300 | 1200 | 4500 | 300 | 6000
AA-03 SUBTOTAL – YEAR 3 ESTABLISHMENT RAW COST | [12 empty] | 6000
★ ADD-ALTERNATE AA-04 – TEMPORARY WATERING (only if Atkinson formally requests in writing)
1 | 32000 | Temporary Water Supply / Connection to Source (allowance) | 1 | LS | 0 | 1 | 2500 | 1500 | 0 | 2500 | 1500 | 0 | 4000
2 | 32000 | Temporary Drip / Soaker System Install & Removal (planting areas only) | 4099 | EA | 0 | 4099 | 1.8 | 1.2 | 0 | 7378.2 | 4918.8 | 0 | 12297
3 | 32000 | Water Truck / Hauled Water (allowance – 8 visits) | 8 | Visit | 0 | 8 | 350 | 280 | 120 | 2800 | 2240 | 960 | 6000
4 | 32000 | Temporary Watering Labor & Monitoring (Year 1) | 1 | LS | 0 | 1 | 0 | 4200 | 0 | 0 | 4200 | 0 | 4200
AA-04 SUBTOTAL – TEMPORARY WATERING RAW COST | [12 empty] | 26497
ADD-ALTERNATE SUMMARY (Raw Costs Before Markup) | [12 empty] | RAW COST
AA-01 – CAVFS Only | [12 empty] | 134409.2
AA-02 – CABS / Bioretention Interface | [12 empty] | 156368.43
AA-03 – Year 3 Plant Establishment | [12 empty] | 6000
AA-04 – Temporary Watering | [12 empty] | 26497
TOTAL ALL ADD-ALTERNATES (if all accepted) | [12 empty] | 323274.63

## Crew Schedule
Project: | SR 510 Yelm Loop
Address: | SR 510 Yelm Loop New Alignment Phase 2
Scope: | SELF-PERFORM LANDSCAPE – Gold Standard (Raw)
Date: | 2026-06-20
SCOPE CATEGORY | DIVISION | CREW COMPOSITION | CREW SIZE | LABOR CLASS | TOTAL LABOR HRS | EQUIP HRS | PRODUCTION BASIS | DURATION (WEEKS) | PERFORM BY | STATUS / NOTE | REF
DIVISION 01 – GENERAL REQUIREMENTS (LIMITED SCOPE)
Mobilization & Demobilization | Div 01 | Foreman + 1 Laborer | 2 | Foreman / Laborer | 16 | – | 1 mob + 1 demob | 0.5 | Self-Perform | Limited scope mob – planting crew only | 01000
Project Foreman – Site Supervision (PLA) | Div 01 | Foreman only | 1 | Landscape Foreman (PLA) | 160 | – | 4 wks × 40 hrs/wk | 4 | Self-Perform | Certified payroll; union rate applied | 01000
Safety Orientation / WSDOT Site Training | Div 01 | All crew | 4 | Mixed | 8 | – | 1-day orientation | 0.2 | Self-Perform | One-time; all trades | 01000
Submittals (plant list, soil amendments) | Div 01 | PM / Admin | 1 | Project Manager | 20 | – | Lump Sum | 0.5 | Self-Perform | Plant list + soil spec only (no hydro/seed mixes) | 01000
Closeout / As-Builts | Div 01 | PM / Admin | 1 | Project Manager | 16 | – | Lump Sum | 0.5 | Self-Perform | Limited scope closeout documentation | 01000
DIVISION 32 – PLANTING (BASE SCOPE)
Plant Layout & Staking (per plan) | Div 32 | Foreman + 1 Laborer | 2 | Laborer / Foreman | 40 | – | ~60 plants/hr/crew located & flagged | 1 | Self-Perform | All plants located before digging | 32000
Upland Plant Mix – Container Stock (2,839 plants) | Div 32 | Foreman + 3 Laborers | 4 | Laborer / Foreman | 189.3 | – | 15 plants/hr/crew (container stock) | 4.3 | Self-Perform | Upland shrubs: 6 species × 2,839 total | 32000
Riparian Plant Mix – Container Stock (1,260 plants) | Div 32 | Foreman + 3 Laborers | 4 | Laborer / Foreman | 84 | – | 15 plants/hr/crew (container stock) | 2 | Self-Perform | Riparian shrubs: 5 species × 1,260 total | 32000
Live Stakes – Willow & Dogwood (408 EA) | Div 32 | 2 Laborers | 2 | Laborer | 41 | – | 10 stakes/hr/person | 1 | Self-Perform | 3 species, hand-driven | 32000
Localized Soil Amendment / Plant Pits (4,099 plants) | Div 32 | Foreman + 2 Laborers | 3 | Laborer / Foreman | 60 | 8 | Manual & mini-excavator spot work | 1.5 | Self-Perform | Per-plant pit soil amendment only (not full-site) | 32000
Mulch Rings / Plant Saucers (4,099 EA) | Div 32 | 2 Laborers | 2 | Laborer | 50 | – | ~50 rings/hr (hand apply) | 1 | Self-Perform | 24" dia × 3" depth per plant only | 32000
Punch-List / Landscape Deficiency Walk | Div 32 | Foreman | 1 | Landscape Foreman | 16 | – | End of planting | 0.5 | Self-Perform | Final walk, tag, and replacement | 32000
PLANT ESTABLISHMENT (BASE – YR 1 + YR 2)
Year 1 Establishment (12 months) | Div 32 | Foreman + 2 Laborers | 3 | Laborer / Foreman | 280 | – | Monthly visits × 12 months | Ongoing | Self-Perform | Watering, weeding, inspection, correction | 32000
Year 2 Establishment (if required) | Div 32 | Foreman + 1 Laborer | 2 | Laborer / Foreman | 180 | – | Bi-monthly visits × 12 months | Ongoing | Self-Perform | Reduced frequency – Year 2 | 32000
Weed Control (18 visits) | Div 32 | 2-man crew | 2 | Laborer | 144 | – | 8 hrs/visit | Ongoing | Self-Perform |  | 32000
Fertilization (4 applications) | Div 32 | 2-man crew | 2 | Laborer | 32 | – | 8 hrs/app | Ongoing | Self-Perform |  | 32000
Plant Replacement (10% allowance) | Div 32 | Foreman + 2 Laborers | 3 | Laborer / Foreman | 60 | – | Allowance | Warranty | Self-Perform | Warranty obligation | 32000
Final Inspection / WSDOT Acceptance Walk | Div 32 | PM + Foreman | 2 | PM / Foreman | 8 | – | 1-day walk | End | Self-Perform |  | 32000
⛔ EXCLUDED FROM REV-04 BASE BID (available as Add-Alternates AA-01 to AA-04)
⛔ Hydroseeding / Full-Site Seeding (all mix types)
⛔ Full-Site 3" Bark Mulch (1,257,578 SF)
⛔ Fine Grading – Landscape Areas
⛔ Topsoil Stripping & Stockpiling
⛔ CAVFS / MVFS (AA-01 if requested)
⛔ CABS / Bioretention Interface (AA-02 if requested)
⛔ Underdrain Piping / Check Dams / Flow Spreaders (AA-02)
⛔ Irrigation (permanent or temporary) – AA-04 if formally directed
⛔ Traffic Control / TESC beyond GS work area
⛔ Civil Earthwork / Year 3 Establishment (AA-03)
TOTAL SELF-PERFORM LABOR HRS (LIMITED SCOPE ESTIMATE) |  |  |  |  | ~1,404 hrs | ESTIMATED FIELD DURATION: ~6–8 weeks (planting) + 24 months establishment

## SUMMARY
Project: | SR 510 Yelm Loop
Address: | SR 510 Yelm Loop New Alignment Phase 2
Date: | 2026-06-20
DIV. NO. | DESCRIPTION | TOTAL DIV. COST | NOTES
BASE BID – LIMITED GOLD STANDARD LANDSCAPE PACKAGE
1 | Planting – Upland Mix, Riparian Mix, Live Stakes, Layout, Soil Amendment, Mulch Rings, Punch-List | 124759.05 | UP + RP + Live Stakes + localized soil/mulch only
2 | Commercial Carry – Scaled to Limited Scope | 46000 | Mob, foreman, cert payroll, submittals, closeout, insurance/bond
3 | Plant Establishment / Maintenance (Yr 1 + Yr 2 in base bid) | 39740 | Yr 3 = AA-03 (not in base bid)
4 | Irrigation / Temporary Watering | 0 | EXCLUDED – RFI-01 CLOSED. Priced as AA-04 if formally directed in writing.
TOTAL RAW PROJECTED COST |  | 210499.05 | Sum of all base bid divisions (before markup)
── MARKUP / PRICING OPTIONS ──
5% | Contingency (5% of Raw Cost) | 10524.9525 | Applied before profit markup
| SUBTOTAL BEFORE PROFIT MARKUP | 221024.0025
20% | OPTION A – 20% MARKUP on Cost | 44204.8005 | 16.7% Gross Profit Margin
| OPTION A – TOTAL BID (20% Markup) | 265228.803
25% | OPTION B – 25% MARKUP on Cost ← 20% GP MARGIN TARGET | 55256.0006 | 20% Gross Profit Margin – RECOMMENDED (Gold Standard target)
| OPTION B – TOTAL BID (20% GP Margin) ← RECOMMENDED | 276280.0031 | ← Gold Standard target gross profit
ADD-ALTERNATES (NOT IN BASE BID – Price separately after applying same 5% contingency + 25% markup)
AA-01 | CAVFS Only (2.66 AC) | 134409.2 | Raw cost – apply 5% contingency + 25% markup for bid price
AA-02 | CABS / Bioretention Limited Interface | 156368.43 | Raw cost – apply 5% contingency + 25% markup for bid price
AA-03 | Year 3 Plant Establishment | 6000 | Raw cost – apply 5% contingency + 25% markup for bid price
AA-04 | Temporary Watering (if formally directed) | 26497 | Raw cost – apply 5% contingency + 25% markup for bid price
TOTAL ALL ADD-ALTERNATES (raw cost if all accepted) |  | 323274.63
✅ DOCUMENT BASIS |  | Rev-04 Basis: Full WSDOT Archive – Plans Vol. 1-4 + Specs Vol. 1-2 + Addenda + Q&A. Quantities confirmed from LSN01 (Sheet 275/635). Rev-04 limited scope per Nathan Petty instructions dated June 2026.
SUBMISSION STATUS |  | NEAR SUBMISSION-READY – Rev-04 Limited Scope. Scope reduced per Gold Standard bonding/risk decision. Add-Alternates AA-01 to AA-04 available upon Gold Standard direction. Date corrected to June 2026.
⚠ INSURANCE / BOND |  | GL Insurance ($4,500) and Bond ($5,000) already in Commercial tab scaled to this package. Do NOT add insurance % again in markup – this would double-count.
⛔ EXCLUDED (BASE BID) |  | Hydroseeding, full-site seeding, full-site bark mulch, fine grading, topsoil stripping, CAVFS/MVFS, CABS, bioretention, underdrain, check dams, irrigation, traffic control, civil earthwork, TESC beyond GS work area.
📌 BID RANGE NOTE: Base Bid alone (Option B) = ~$274K, which is BELOW Nathan's $300K floor on its own. The $300K–$500K target is met for the overall submitted package only when at least one Add-Alternate is included: Base Bid + AA-01 (CAVFS) = ~$450K (within range). Base Bid + AA-01 + AA-02 = ~$656K (exceeds range). Gold Standard must select AA-01 at minimum to land in the requested range, or confirm a base-bid-only submission is acceptable.